## Sheet1
Date | Task | Time (h)
16.06.2019 | Reseaching various backend technologies such as Django and Flask, and how to make them work with React | 4
16.06.2019 | Created the repo | 0
16.06.2019 - 20.06.2019 | Working out how to use SQLAlchemy with Flask and trying to get a minimal api working with one simple database table along with Marshmellow | 6
20.06.2019 | Added a working full list of card objects to the API. Can also return single card object by their ID | 3
22.06.2019 | Also added the full mtg set data to the API is a similar way | 1.5
24.06.2019 - 26.06.2019 | Working out how to connect backend with a minimal frontend app with proxy | 3
26.06.2019 - 27.06.2019 | Researching and testing Material-ui styles, tables and poppers and other related components for presenting lists of cards and their respective images | 6
28.06.2019 | Card image Popper now opens up nicely above the card text line when hovering the mouse over it | 3
01.07.2019 - 04.07.2019 | Fixed erros and reseached&tested better ways of applying Material-ui styles to custom components | 6
04.07.2019 | Added fonts for displaying various Mtg symbols such as manacosts and card types | 1
05.07.2019 | Added a component to correctly display cards' manacosts | 2
08.07.2019 | The Card objects from the api are now returned paginated with additional info such as the link for the next page and the total number of cards and pages. This is because the json for all the cards is too big and slow. | 1.5